## Slide 1: Oracle E-Business Suite (EBS) 12.2 Project Change Management Plan for Cutover and Outage
Notes: Version Control:
V10 Added an asterisks with content on slide #17.
V0.9 Changes made to slide #18. The comments column was updated for the following three systems: Aurora (FAS), FIFA (Aurora Faculty), and Wasabi (SPH)
V0.8 Two changes: 1. Removed slide #25 which had duplicate data as slide #9. 2. Update slide #9 with two items: 1) Updated URL for Manual Validation process for GL Validator and 2) Removed 7-segment note
V0.7 Changed 1) the Oracle support end date from 2033 to 2034 on slide #24, 2) Added “Stopping scheduled jobs on Monday, 4/17 at 5pm” for Harvard Training Portal on slide #18
V0.6 Added the last bullet point to Concur slide #15
V0.5 Updated date status on timeline for slide #4
V0.4 Updated March 1. 2023: Added Release Notes link on Finance page on slide #22
V0.3 Updated February 15, 2023: 1) Added FINFILER server name and IP address to slide #10, 2) Added a table with details on the user changes needed for Chart (GL) Validation on slide #9
v0.2 Updated February 7, 2023: 1) Updated slide #16 with new HART availability, 2) Added new slide #25
v01 December 9, 2022: New presentation file created

## Slide 2: Meeting Objectives
Introduce ITCRB Project Timeline | 
Cutover & Outage Plan | 
System Map & Business Impact Analysis | 
Next Steps | 

## Slide 3: EBS 12.2 Project
Implementation Cutover and Outage Plan Discussion
Notes: To set a different background color: select Format in menu > select Slide Background > choose Fill type and color

## Slide 4: ITCRB Project Timeline
Jul/Aug 2021
May 2020
Proposal Approved
Initial Amount $800,000
Planning Phase: 10 months
Implementation: 12 months
Sept 2021/ Mar 2022
Proposal
Initial discovery, planning, design & retrofit
Iterative testing, implementation and stabilization
Testing Phase 3
Functional
Interface/APIs
Workflow
User Security
Reporting
Change Request #1
Total funds $1.2M
Paused due to workload
Continued technical activities
Resumed
Architecture Design
Impact Assessment
Discovery from Planning Phase
Findings
New scope added: CloudShield 2.0
Excluded OCI and MSP as solutions
Apr 2021
Deep Dive Resource and Capacity Planning and Retrofit Work
Workstream Planning
Created project resource plan
Identified gaps
Retrofit work Oct-Mar 2022
Change Request #2
Total Funds: $2.4M
Implementation: 19 mos
Feb 2022
Mar-Jul 2022
Today
Sep 2020
Planned Cutover
Cutover from 12.1 to 12.2
Outage: Tuesday 4/18 (5PM) through Monday 4/24 (8AM)
Apr 2023
Testing Phase 2
Functional
Interface/APIs
Workflow
User Security
Reporting
Testing Phase 1
Functional
Interface/APIs
Workflow
User Security
Reporting
Jul-Nov 2022
Nov 2022-Mar 2023
Soft Pause
Change Request #3
Total Funds: $2.4M
Implementation: 21 mos
Sep 2022
Stabilization Phase
May-June
Retire 12.1 Oracle stack
Jun 2023
Notes: Soft pause, during this time we covered the technical activities and technical analysis

## Slide 5: Cutover and Outage Schedule
When is the outage for Oracle E-Business Suite (EBS)?
  Tuesday 4/18/2023 (5PM) through Monday 4/24/2023 (8AM)
  Additional details about this week:
    Patriot’s Day is on Monday (4/17)
    3Q Quarter close is complete (4/14)
    School vacation week
How were the outage dates selected?
  Reviewed potential weekend dates from March – June 2023
  Analysis on key events and pros/cons for each weekend
  Preference to begin new system usage on a Monday
  Groups involved in selecting date are: FAR, Strategic Procurement, OTM, OSP, HUIT, Financial Systems Executive Committee, Financial Systems Leadership Group

## Slide 6: Oracle EBS is the Center of Financial Processing
EBS
B2P
Financials Data Warehouse
HART
Card Processing (PCard)
HR Systems
Fieldglass
TouchNet eCommerce
Concur (T&E)
Sponsored Research
Other (Wasabi and School Interfaces)
HUBS
ADVANCE
my.harvard
CPATH

## Slide 7: High-level System Impact Map
System | Availability | Comments / Notes | Detail slide #
Oracle EBS/Financials | None | No outgoing feeds during the outage; incoming feeds sent during the outage will be processed prior to Monday. Normal processing resumes on Monday 4/24. | 8-12
B2P | None | System is unavailable; see slide #13 for details | 13
Financials Data Warehouse | Partial | Available Wed-Fri with data as of Monday 4/17. Partial due to system not available on Sat-Sun. No impact to HR data and QlikView. | 14
Card Processing (PCard) | Partial | See detail slide #15 | 15
Concur (T&E) | Partial | See detail slide #15 | 15
HART | Available | See detail slide #16 | 16
Sponsored Research | Available | Data updated as of Monday 4/17. Includes GMAS, PI Dashboard and eCRT | 17
HR Systems | Available | No costing changes. (Valid strings created but never used will work). See additional slide for details on Aurora, Harvard Training Portal, PeopleSoft modules, Wasabi, etc. | 18
my.harvard | Available | Data updated as of Monday 4/17 | 19
HUBS | Available | Actuals as of Monday 4/17, no CCID Validation | 20
CPATH | Available | Data from CAPS as of Tuesday 4/18 | 
Fieldglass | Available | No costing changes | 
TouchNet ECommerce | Available |  | 
ADVANCE | Available | Files sent to GL during 4/18-4/24 will not be processed. No new COA information will be available. | 
Other (Wasabi and School Interfaces) | Available | No costing changes and no new COA information will be available. Journals transmission will not be available. (interface with other systems besides PeopleSoft) | 

## Slide 8: Oracle Outage Impact: Oracle EBS/Financials
The following Oracle EBS Financials modules will be offline:
Accounts Payable
Accounts Payable Adjustment Form for Assets
Accounts Receivable - (see details on slide #11)
CAPS
Cash Management (CMRA)
Chart Security Maintenance Application (CSMA)
Chart of Accounts (COA) - (see details on slide #9)
Fixed Assets - (see details on slide #12)
General Ledger
GL-PCR
iPro Requisition History Inquiry
iReceivables & Collections
Web ADI
Web Reimbursement History Inquiry
Notes: If you have any questions please contact ithelp@harvard.edu

## Slide 9: Oracle Outage Impact: Oracle EBS/Financials - Chart Validation
All Chart Validation is offline which includes:
Chart of Accounts (COA) – Batch Validation
Chart of Accounts (COA) – Web Service / GL Validator
Chart of Accounts (COA) – Chart Validator Web Page
Chart of Accounts (COA) – Apigee API
Systems using these services need to change their URL to:
GL Validator URLs |  |  | 
Type | Change | Access Method | Oracle EBS R12.2 Value
Apigee URL | No Change | URL | https://go.apis.huit.harvard.edu/ats/fin-coa-validator/v1/
Manual Validation | Yes - use new URL | URL | https://finprod.huit.harvard.edu:8000/OA_HTML/OA.jsp?page=/oracle/apps/huicx/huglCoaVal/webui/huglCoaValPG
Direct EBS URL | Yes - use new URL | URL | https://finprod.huit.harvard.edu:8000/OA_HTML/hu_coa_webval.jsp
APEX URL | Yes - use new URL | URL | https://finprod.huit.harvard.edu:8052/ords/f?p=COAVAL
Bulk COA Validator - Excel Macro Sheet | Yes - Download latest file | Excel File | https://oracle.fss.finance.harvard.edu/general-ledger-user-guide
GL Validator | Yes – use new URL | URL | https://finprod.huit.harvard.edu:8052/GLValidate/ValidateGLAccount
Notes: If you have any questions please contact ithelp@harvard.edu

## Slide 10: Oracle Outage Impact: Oracle EBS/Financials – Feeders
FMS Developers will contact Feeder Primary Contacts between Jan-Mar 2023 to coordinate testing.
FINFILER
Tuesday 4/18 5pm: Current FINFILER goes offline and email sent to Primary Contacts Tuesday 4/18 8pm: New FINFILER online and email sent to Primary Contacts Wed-Sun 4/19-23: Update FINFILER PROD settings New server name and IP address Name: finfiler-prod2.huit.harvard.edu IP-Address: 10.139.110.155 Subnet: 10.139.110.128/26 Update scripts with new server name and IP address
ASFTP
No server changes Users can upload file(s) to their same location as they currently do Notifications: Normal notification process used
Notes: If you have any questions please contact ithelp@harvard.edu

## Slide 11: Oracle Outage Impact: Accounts Receivable
All Bills need to be entered into Oracle AR by 3pm on Tuesday 4/18
Last Bill Run on Tuesday 4/18 at 4pm
Next Bill Run as scheduled on Wednesday 4/26

## Slide 12: Oracle Outage Impact: Fixed Assets & Inventory
During Outage April 18th 5pm through Monday April 24th 8am:
  No Access to the Asset Workbench
  No Fixed Assets reporting
  No updating inventory inside of Oracle
  No Asset Mass Uploads
  No Mass Additions

## Slide 13: Oracle Outage Impact: B2P
The Buy-to-Pay system will be unavailable effective 5PM on April 18th.
This includes the ability to view/search in B2P, and all Accounts Payable, Supplier Onboarding, Requisitioning/PO/PR/NR, Contract Management, and Sourcing activities and functionality.
Key Activities | Dates
Supplier Onboarding, Maintenance, & Reactivation (New requests or supplier updates) | Wednesday, April 12th 5PM
Non-standard Check Processing (Special Handling) | Monday, April 17th 5PM
PR/NRs that must be paid prior to outage should be approved by end of day. | Monday, April 17th 5PM
Final payments before outage (Includes Zelle, check, Paymode) | Tuesday, April 18th
All requisitions must be fully approved by 4:30 to have a PO created before outage. | Tuesday, April 18th 4:30PM
Notes: PR = Payment Request
NR = Non-employee Reimbursement

## Slide 14: Oracle Outage Impact: Financials Data Warehouse (CENDW) Schedule & Details
Dates | Days | Updates
4/17 | Monday | Last data refresh in Data Warehouse on Monday night
4/18 | Tuesday | Transactions go into EBS but Data Warehouse is not loaded with Tuesday (4/18) data
4/19-21 | Wednesday – Friday | No new transactions in EBS (Data Warehouse is not re-loaded)
4/22-23 | Saturday - Sunday | Outage (not available for export and direct database users but is available for HART users)
4/23 | Sun night | Data Warehouse nightly load runs at 8pm and includes transactions from Tuesday (4/18)
4/24 | Mon 8am | Data Warehouse available and refreshed
Notes: If you have any questions please contact Arun Deshpande

## Slide 15: Oracle Outage Impact: Concur (Expense & PCard)
During the outage, Concur users will still be able to create, submit, and approve Expense and PCard Statement Reports in Concur.
Payments and postings to the GL will not occur during the outage but will resume on a normal schedule starting Monday 4/24 at 8AM.
  Includes payments to Citibank and out-of-pocket reimbursements to individuals
 | Due by
Concur Expense Reports must be fully approved with no exceptions to be paid prior to the outage | Friday, April 14th, 5PM
Concur Statement Reports (PCard) must be submitted and fully approved to post to the GL | Monday, April 17th, 5PM

## Slide 16: Oracle Outage Impact: HART
User Community | Reports/Data | Tues 4/18-Sun 4/23 | Comments/Notes
HART Financial and Grants Management Enterprise Dashboard Users | All dashboards containing data from the financial data warehouse | Data as of 4/17 is available 4/18-4/24 Users are discouraged from running dashboards from Friday, 4/21 8 pm-Monday, 4/24, 8 am | Users may see error messages and inconsistent data while the dashboards are being updated from Friday, 4/21 8 pm-Monday, 4/24, 8 am
HART Self Service Financial and Grants Management Users | All data pulled from the financial data warehouse | Data as of 4/17 is available 4/18-4/24 Self-service users are discouraged from pulling data from Friday, 4/21 8 pm-Monday, 4/24, 8 am. | Users that connect directly to the financial data warehouse with personal credentials will be locked out of database 4/21, 8pm-4/24, 8 am Users using HART subject areas may see error messages and inconsistent data while the dashboards are being updated from Friday, 4/21 8 pm-Monday, 4/24, 8 am
HART FAS Data Hub Dashboard | All financial data found on dashboard; rest of dashboard not affected | Data as of 4/17 is available 4/18-4/24 | Financial data derived from IVY; same impact as Direct Database Users below
Direct Database Users and Export Accounts outside of HART | All data pulled from the financial data warehouse | Data as of 4/17 is available 4/18-4/24 Users will be locked out of the database from Friday, 4/21 8 pm-Monday, 4/24, 8 am | For communities that use tools other than HART to pull data from the financial data warehouse.
HART will be available throughout the EBS 12.2 Upgrade

## Slide 17: Oracle Outage Impact: Sponsored Research*
System | During 4/18 - 4/24 Outage | During the Oracle Financial Outage
GMAS | All systems are up and running Data up-to-date through 4/17/2023 (no new updates 4/18-23) | No new sponsored/GMAS accounts can be set up during the outage (segment revisions can be completed, but any new/modified accounts will not be sent until 4/24/2023 Sponsored budgets will not be sent to the GL until 4/24/2023 Interim financial deliverables with “deliverable period end dates” of 03/31/2023 or prior will be processed normally Final financial deliverables can be processed if journal adjustments have been documented and a final figure has been identified For sponsored payments, receipts can be created and receivables can be updated, however payments will not post to the GL until after the outage is complete No letter of credit (LOC) draws will occur during the outage, but draws will resume their normal schedule after the outage is complete
PI Dashboard |  | PI Dashboard up and available
eCRT |  | eCRT up and available
*All other Research Administration and Compliance Systems (Research Administration Portal, ESTR-IRB, Agreements-DUA, Data Safety, OAIR) will be available and
will not be impacted throughout this update period.

## Slide 18: Oracle Outage Impact: HR Systems
Availability: Available
Comments: No costing changes.
Applications / Services | Comments / Notes
PeopleSoft Absence Management | No impact
PeopleSoft Time & Labor | RapidTime Online Page - Will not be available for combinations not used before RapidTime Upload – Existing costing will work and new costing will reject Adjust Time Page - Will not be available for combinations not used before User error message: “Integration gateway external system contact error…”
PeopleSoft Payroll | Additional Pay Page - Will not be available for combinations not used before Additional Pay Upload – The full file will fail if any new combinations that did not previously exist Additional Pay Form - Will not be available for combinations not used before Payline Transaction Form - Will not be available for combinations not used before
PeopleSoft Costing | Costing Upload – The full file will fail if any new combinations that did not previously exist Manage Costing Page - Will not be available for combinations not used before Employee Costing Direct Data Entry - Will not be available for combinations not used before
PeopleSoft Workforce Administrator (HR) | Quick Hire - Will not be available for combinations not used before Job Data Change Forms - Will not be available for combinations not used before Manage Position - You will not be able to use combinations that have not been previously used. You will receive an error message upon saving with a GL Validator reference and unable to save the page.
PeopleSoft Benefits | No impact
Harvard Careers (replaces ASPIRE) | No impact
Harvard Training Portal | Users can register for classes regardless of costing code but expect email delay of confirmations Stopping scheduled jobs on Monday, 4/17 at 5pm
Aurora (FAS) | Writes to PeopleSoft directly and uses COA Validator; users will get error message for new costing
FIFA (Aurora Faculty) | Uses COA Validator and users will get unavailable message but doesn’t stop generation of files
Wasabi (SPH) | Writes to PeopleSoft directly and uses COA Validator; users will get error message for new costing

## Slide 19: Oracle Outage Impact: my.harvard (Student Information Systems)
Modules | Comments / Notes
SIS (Campus Solution Module) | Data updated as of 4/17
SIS (Financials Module) | Create item type functionality and create scholarship group functionality will generate error messages due to chart validation being offline. Low traffic period and we will reach out to users for follow-up with any issues.
SIS Data Warehouse | 

## Slide 20: Oracle Outage Impact: HUBS (Budget)
Some Jobs that load data and new members into HUBS will not be processed, so the following will not be loaded to HUBS during the EBS 12.2 Upgrade outage:
GL Chart sourced dimension members (i.e., new Act-Subs, Funds, Roots, etc. will not be loaded)
GL actuals that come from HDW (i.e., new Actual data will not be loaded)
Employees from EBS (i.e., new Position/Employee dimension members and data will not be loaded)
In the HUBS Admin Utilities, the following will be disabled during the EBS 12.2 Upgrade outage:
CCID Validation
UDF Fact File Uploads
Notes: If you have any questions please contact hubs@harvard.edu

## Slide 21: Oracle Outage Impact: General Business Processes
Business Process | Last Run in EBS 12.1 | Available in EBS 12.2 | Comments
General Ledger Journal Processing | Tuesday, 4/18 @ 5pm | Monday, 4/24 | Includes ADI, Feeders, Manual and GL-PCR
Payroll Journals for Check Date | See Comments column | See Comments column | GL files for weekly and biweekly payrolls as well as any off cycle payrolls On cycle GL will run on 4/19 but will not feed to the GL until 4/24 Off cycle GLs will run ad hoc but will not feed to the GL until 4/24 No impact to Monthly GL file
Security Maintenance | Monday, 4/17 @ 12pm | Monday, 4/24 | No new user access requests/changes/updates will be processed.

## Slide 22: Next Steps
Incorporate any changes and feedback from stakeholders
Capture questions in project change management FAQs
Continue to update system outage with new details
To learn more, see our Release Notes

## Slide 23: Appendix

## Slide 24
Oracle E Business Suite 12.2 Upgrade Vision |  | 
Enterprise Financial Systems aspires to upgrade to the latest version of the Oracle eBusiness Suite that guarantees premier support from Oracle through at least 2034. |  | 
Objectives |  | Measurable Benefits
Upgrade Oracle eBusiness application suite to 12.2 on an improved cloud infrastructure Continue to receive Oracle E-Business Support including patches through 2034 Position Harvard to take advantage of new functionality offered on an incremental basis |  | Successful upgrade in all non-prod and Prod environment with minimal issues Remain current, secure and supported by Oracle Deliver application updates and functionality to end user community through monthly and quarterly release
Guiding Principles |  | 
Engage with functional and central stakeholders along with external vendors to minimize disruption to current services provided Project and post implementation will leverage existing internal support services Eliminate technical debt where possible including customizations that can be replaced by functionality available in the newer version; take advantage of Cloud technologies Reduce or contain operating costs through architecture improvements The decision to stay with Oracle as a vendor and upgrade the existing E-Business Suite instead of moving to a SaaS model has been discussed and approved by Financial Administration Systems Leadership and Executive Committees |  |